## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | ZL; 10/5/21;
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | ZL; 10/5/21;
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | ZL; 10/5/21;
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | ZL; 10/5/21;
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | ZL; 10/5/21;
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | ZL; 10/5/21;
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | ZL; 10/5/21;
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | DP; 10/5/21
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | DP; 10/5/21
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | DP; 10/5/21
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | DP; 10/5/21
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | DP; 10/5/21
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | DP; 10/5/21
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | DP; 10/5/21
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | DP; 10/5/21
As a player When I move a normal piece makes it the furthest row away from the play, the piece will become kinged | Given a piece reaches the other side when when i move it then the piece is promoted to a king |  |  | Pass | QR; 10/26/21
a piece can move adjacently one square forward diagonally from the player (only on dark squares) | **Given** there us a valid square next to a piece **when**the player moves the piece **then** the game updates an the piece is moved |  |  | Pass | QR; 10/26/21
| **Given** a piece is a king, **when** this piece moves backwards to legal space, **then** it will move there. |  |  | Pass | QR; 10/26/21
As a player I want to be able captures an opponent’s piece by jumping over it | **Given** that I have selected a valid move **when** I jump over a piece, **then** I expect my piece to move to capture the other piece. |  |  | Pass | QR; 10/26/21
As a player I want to capture pieces by Jumping over multiple pieces in one move | **Given** a piece can move multiple times **when** the user can jump again**then** they are prompted if they would like to do so |  |  | Pass | QR; 10/26/21
follows same rules as other pieces, but kings can move forward and backwards diagonally to adjacent squares across the board | **Given** that I have a king piece **when** I want to move that king piece **then** I expect that I can move that piece backwards diagonally to adjacent squares. |  |  | Pass | QR; 10/26/21
As a Player I want to be able to load a game so that I can load one of the saved boards from my account. | [5 empty] | Pass | QR; 11/12/21
The Player must be able to resign (forfeit) any game he is playing. | **Given** two players are on a game, **when** I press resign, **then** both players are shown game over message and can press exit button to be sent to the homepage. |  |  | Pass | QR; 10/26/21
As a Player I want to be able to pause a game so that I can play it later, this should save the board to my account. Also, as a Player I want to be able to resume a game so that I can continue playing a game that I paused earlier. | [5 empty] | Pass | QR; 11/12/21
A player must be able to select a difficulty to play against for practice, for example easy, medium, hard | [5 empty] | Pass | QR; 11/12/21